## Executive Overview
DeltCRM Multi-Product Platform & Integration Roadmap
Master Status & Architectural Overview · Contract Version 1.0
Key Summary
Architecture Model | Multi-product SaaS platform with centralized Control Plane (Platform) and independent Data Planes (HRMS, POS, Mail).
Customer Experience | Unified single sign-on, one tenant domain (e.g. acme.blufield.cloud), shared AppShell, unified billing, isolated products.
Contract Status | COMPLETED & VERIFIED (@deltcrm/product-contracts v1.0.0 with OpenAPI, JSON schemas, typed clients, RS256 token verification).
Platform Integration Status | Phase 1 (Contracts & Boundaries) 100% Done. Phase 2 (Control Plane) in progress.
Core Monorepo Sprints | Sprints 1-5, 6.5, 7 Complete. Sprint 6, 7.5, 8 currently in progress toward General Availability (GA).
Ownership & Boundary Matrix
Component / Layer | Owning Scope | Authoritative Data & Responsibilities | Communication Channel
Platform (Control Plane) | Central Platform Team | Tenant lifecycle, user identity/SSO, subscriptions, product entitlements, global navigation, audit outbox | Gateway routing (/app, /api/platform) & RS256 Tokens
HRMS (Data Plane) | HRMS Product Team | Employees, organization structure, shifts, attendance calculation, leaves, payroll | Gateway (/app/hrms, /api/hrms) + Internal Service Client
POS (Data Plane) | POS Product Team | Catalog, inventory, store locations, registers, sales orders, payment processing | Gateway (/app/pos, /api/pos) + Internal Service Client
Mail (Data Plane) | Mail Product Team | Mailboxes, email messages, communication templates, broadcast campaigns | Gateway (/app/mail, /api/mail) + Internal Service Client
Product Contracts | Shared Architecture Gate | JSON Schemas, OpenAPI 3.0, TypeScript generated clients, Token Claims, Event Envelopes | Published npm package: @deltcrm/product-contracts

## Platform Integration Roadmap
DeltCRM Multi-Product Platform Integration Roadmap
Architecture Plan for Connecting Independent Services to the Platform
Phase | Phase Name | Objective & Scope | Key Technical Deliverables | Dependencies | Status | Target / Exit Criteria
Phase 1 | Contracts & Boundaries | Define formal data boundaries, schemas, manifests, and typed clients between Platform and product services. | • @deltcrm/product-contracts v1.0.0 package • JSON schemas (manifest, token, entitlements, events, errors) • OpenAPI 3.0 specs and generated TypeScript client • ADRs 001-005 and extraction safety readiness docs | None (Baseline) | COMPLETE | 100% test pass on contracts, schemas, and token validation guards.
Phase 2 | Platform Control Plane | Implement central identity token issuance, entitlement engine, and service-authenticated sync endpoints. | • RS256 / JWKS token issuance with aud: <product>-api • Service credential verification (X-Product-Key) • Synchronous identity-status & entitlement API • Transactional outbox relay & dead-letter queue | Phase 1 Contracts | IN PROGRESS | Platform issues verifiable tokens and handles internal queries.
Phase 3 | Unified Web Entry & Gateway | Establish unified tenant routing at gateway and shared frontend design system / shell across products. | • Nginx / Cloud Gateway path-based routing (/app/{product}) • Shared @deltcrm/app-shell and @deltcrm/design-system • Tenant subdomain mapping (e.g. acme.blufield.cloud) • Unified language routing (en/ar) and error states | Phase 2 Control Plane | PLANNED | Seamless UI navigation between Platform, HRMS, and other services.
Phase 4 | HRMS Service Extraction | Decouple HRMS domain from Platform monolithic code into an independent service without data loss. | • HRMS database schema isolation • Production data reconciliation and non-destructive backfill • Service deployment behind /app/hrms and /api/hrms • Employee, Attendance, Leave, Payroll workflows verified | Phase 3 Gateway | PLANNED | HRMS operates as an independent service consumed via contracts.
Phase 5 | POS & Mail Product Onboarding | Onboard external POS and Mail repositories using the standardized integration contracts and manifests. | • Standardized product repository templates • Manifest registration (permissions, routes, webhooks) • Subscription lifecycle consumers (provision/suspend) • Multi-product tenant billing & entitlement verification | Phase 4 Extraction | PLANNED | Full multi-product suite live on unified tenant portals.

## Sprint Delivery Roadmap
DeltCRM Monorepo Sprint Delivery Roadmap (Sprints 1–9)
Detailed Feature Delivery Schedule aligned to ERD v4 and Monorepo Architecture
Sprint | Sprint Title | Target Outcomes & Delivered Capabilities | Primary Screens & APIs | Complexity | Status | Exit Gate & Verification
Sprint 1 | Organization & Administration | Tenant hierarchy, departments, designations, employee directory, quota enforcement with advisory locks, CSV bulk import with BullMQ, user invites & RBAC matrix. | B1 Wizard, B3 Org Builder, B4 Employee Directory, B6 CSV Import, B7/B8 Role Matrix | Medium (2-3w) | COMPLETE | Seeded 150 employees via CSV, RLS tenant isolation verified, zero cross-tenant leak.
Sprint 2 | Platform Owner Core & Operations | Platform control plane, tenant provisioning, system roles, transactional outbox relay, BullMQ worker entrypoint, audit logging and system health. | S1-S4 Tenant Administration, S9-S11 Health & Audit Logs | Large (3-4w) | COMPLETE | Outbox crash recovery verified, dual connection pool (app_user/app_admin) operational.
Sprint 3 | Business Admin & Attendance Config | Business Admin web portal, hierarchical policy resolver (employee > department > tenant), shift scheduling (overnight aware), rosters, geofences, office holidays. | B1-B9 Tenant Admin, H4 Geofence Editor, H5 Policies, H6 Shifts, H7 Rosters, H8 Holidays | Medium (2-3w) | COMPLETE | Deterministic policy resolution verified across overnight shifts and custom holiday scopes.
Sprint 4 | Attendance Core & Web Runtime | Deterministic AttendanceCalculator (60+ table-driven cases), AttendanceDay aggregate, web punches, daily finalizer cron, live muster register. | H1 Shared Dashboard, H9 Live Register, H10 Employee Detail & Timeline, H13 Exceptions | Large (3-4w) | COMPLETE | 60+ calculation edge cases pass (overnight, breaks, half-days, grace periods, OT).
Sprint 5 | Mobile Trust & Verification (MVP) | Trusted employee mobile attendance punches with device integrity, root detection, mock-GPS defense, face capture/liveness verification, geofence radius check. | M1-M13 Mobile Punch Screens, M19-M20 Trust Alerts, H14 Security Alerts | Large (3-4w) | COMPLETE (MVP) | Mock GPS, spoofed face, and out-of-bounds punches fail-closed and log security alerts.
Sprint 6 | Field Tracking & Offline Sync | Background location streaming for field staff, offline punch storage with tamper-resistant replay, live map tracking and route playback. | H2-H3 Live Field Map, M16-M17 Offline Sync & Timeline | Medium (3-4w) | IN PROGRESS | Offline punch queue survives app kill and replays chronologically with server-side validation.
Sprint 6.5 | Dynamic Tenant Runtime & Branding | Dynamic tenant module resolution, attendance capability configuration, theme & brand token customizer, English & Arabic locale switching. | M2-M6 Dynamic Mobile Navigation, Modules/Attendance Config, Theme Studio | Medium (2-3w) | COMPLETE | 1,308 localization keys synchronized; LTR/RTL dynamic rendering across all screens.
Sprint 7 | HR Operations, Leave & Regularization | Attendance regularization requests & manager approval hierarchy, leave management & balance tracking, employee notifications, monthly payroll lock snapshot. | H11 Regularization, H12 Approvals, H15 Reports, H16 Payroll Lock, L1-L3 Leave Workflow | Medium (2-3w) | COMPLETE | Regularization & leave approval changes recalculate AttendanceDay aggregates deterministically.
Sprint 7.5 | HR Portal Reconstruction | Rebuilding the unified Tenant HR Portal around 5 intuitive pillars: Dashboard, Employees, Modules, Reports, and Settings with full Arabic RTL support. | Complete Tenant HR Portal navigation and workflows (Dashboard, Employees, Reports, Settings) | Large (3-4w) | IN PROGRESS | 155 clean routes, 0 hardcoded colors, 100% accessible navigation and role gating.
Sprint 8 | Billing, Revenue Ops & GA Gate | Subscription tiers, dynamic regional currency pricing, quota limits, invoice generation, payment gateway integration, security audit and GA release. | S5-S8 Platform Billing & Invoicing, B10 Tenant Subscription, A2-A3 Self-serve Signup | Large (4-5w) | IN PROGRESS | Zero security vulnerabilities, non-destructive migration verified, automated disaster recovery.
Sprint 9 | Modular Architecture & Contracts Freeze | Hardening module boundaries, establishing public contracts and isolated CI pipelines for POS, Mail, and third-party developer teams. | Developer SDKs, OpenAPI portal, automated package publishing and dependency boundary CI | Medium (3-4w) | PLANNED | Isolated product teams can build, test, and release without affecting other modules.

## Contract Integration Guide
How to Use @deltcrm/product-contracts in Your Project
Step-by-Step Technical Guide for Connecting a Product Service to DeltCRM Platform
Integration Checklist & Steps
Step # | Integration Step | Required Action / Implementation | Contract Entity / Schema | Security & Validation Rule
1 | Install Contracts Package | Add package to project dependencies: pnpm add @deltcrm/product-contracts | @deltcrm/product-contracts v1.0.0 | Use published package only; never copy types or write ad-hoc clients.
2 | Define Product Manifest | Create manifest file (e.g. manifests/pos.v1.json) declaring product key, name, version, frontend routes, API paths, health checks, and permissions. | product-manifest.schema.json ProductManifest interface | Product key (e.g. 'POS', 'MAIL') and declared permissions are immutable once deployed.
3 | Authenticate Inbound Requests | Validate incoming RS256 Bearer JWT product token on every product API endpoint. Verify tenantId, userId, membershipId, audience, and expiration. | product-token.schema.json ProductTokenClaims ProductTokenVerificationKey | Reject tokens where audience does not match your service (e.g. 'pos-api') or tenantId does not match request context.
4 | Verify Real-time Identity & Entitlements | Initialize ProductIntegrationClient with platform internal URL and service key. Query platform before fulfilling sensitive actions. | ProductIntegrationClient getIdentityStatus() getEntitlements() | Never cache tenant entitlement state indefinitely. Fail closed if tenantStatus !== 'ACTIVE' or product is disabled.
5 | Consume & Publish Async Events | Listen to platform lifecycle events (tenant provisioned, suspended, subscription changed). Publish product events via transactional outbox. | event-envelope.schema.json ProductEventEnvelope platform.product.activation-requested.v1 | All event consumers must be idempotent (using eventId). Handle retries and route failures to dead-letter queues.
6 | Connect Frontend via AppShell | Wrap product UI pages in the shared DeltCRM AppShell. AppShell handles top bar, sidebar, tenant branding, language switching, and user profile. | navigation.schema.json @deltcrm/app-shell @deltcrm/design-system | Product pages mount at /{locale}/app/{product_key}/* without iframe isolation.
Synchronous Internal Platform Endpoints
HTTP Method | Path | Required Headers | Response Contract | Description
POST | /product-integration/token | Authorization: Bearer <session_token> | ProductTokenResponse | Exchange a valid platform session for an audience-specific product JWT token.
GET | /internal/v1/tenants/:tenantId/users/:userId/identity-status?membershipId=:id | X-Product-Key, X-Product-Service-Key | ProductIdentityStatus | Check real-time lifecycle status of tenant, user, and workspace membership.
GET | /internal/v1/tenants/:tenantId/entitlements | X-Product-Key, X-Product-Service-Key | EffectiveEntitlements | Retrieve active products, capabilities, feature flags, and numerical quotas.
GET | /product-integration/navigation | Authorization: Bearer <token> | NavigationContract | Retrieve dynamic navigation menu filtered by user's assigned permissions and entitlements.
GET | /internal/v1/tenants/:tenantId/products/:productKey/status | X-Product-Key, X-Product-Service-Key | ProductProvisioningStatus | Query current asynchronous provisioning and activation status for a product.